01 Project Charter

Project Name: ABC Electronics Odoo ERP Implementation

Client: ABC Electronics Pvt Ltd

Industry: Electronics Wholesale and Retail

Document Version: 1.0

1. Document Purpose & Explanation

The Project Charter is the foundational document that formally authorizes the existence of the ERP implementation project. It provides the project manager and functional consultant with the authority to apply organizational resources to project activities.

Business Reasoning: Before any software is configured, executive leadership and the implementation team must be in 100% alignment regarding what the project will achieve, how long it will take, and what falls outside the project's boundaries. This prevents "scope creep" and ensures a clear metric for success.

Consultant Activities:

- Conduct initial executive alignment meetings.

- Draft the high-level project boundaries and timelines.

- Identify core stakeholders and their authority levels.

- Secure formal sign-off from the project sponsor.

2. Executive Summary & Business Challenges

ABC Electronics Pvt Ltd currently relies on a fragmented ecosystem of Excel spreadsheets, disjointed basic accounting software, and manual email workflows to manage its Wholesale and Retail operations.

Identified Business Pain Points:

- Inventory Blind Spots: Lack of real-time synchronization between warehouse stock and sales commitments results in frequent stockouts or overselling.

- Inefficient Order-to-Cash: Manual generation of quotations and invoices leads to heavy administrative overhead and high human-error rates.

- Procurement Delays: No automated alerts for low stock, leading to delayed purchase orders and lost revenue opportunities.

3. Project Objectives

The objective of this project is to implement Odoo ERP as a centralized system of truth.

- Objective 1: Achieve 100% real-time visibility into inventory levels across both retail and wholesale channels.

- Objective 2: Reduce quotation-to-invoice processing time by 40% through automated document generation.

- Objective 3: Implement a standardized Procure-to-Pay workflow to ensure stock optimization.

4. Project Scope

In-Scope Modules:

- CRM: Lead tracking, pipeline management, and activity scheduling.

- Sales: Quotation generation, price lists, and sales order confirmation.

- Purchase: Vendor management, RFQs, and automated purchase orders.

- Inventory: Warehouse setup, inbound/outbound stock movements, and valuation.

- HR (Employees): Basic employee directory and departmental hierarchy.

- Accounting: Core workflows for Customer Invoicing (A/R) and Vendor Bills (A/P).

Out-of-Scope (Phase 1):

- Manufacturing (MRP)

- E-Commerce Website Integration

- Advanced Payroll Processing

- Point of Sale (POS) Hardware integration

5. Stakeholder Analysis

| Name | Role / Title | Project Responsibility | Authority Level |
| --- | --- | --- | --- |
| Nowfal | Administrator | Ultimate sign-off, budget approval. | High |
| Rahul Sharma | Sales Manager | SME for CRM & Sales processes. | Medium |

6. High-Level Timeline & Milestones

- Milestone 1: Project Kickoff & Charter Sign-off (Week 1)

- Milestone 2: Requirements Gathering & Process Mapping (Week 2)

- Milestone 3: System Configuration & Master Data Import (Week 3-4)

- Milestone 4: User Acceptance Testing (UAT) (Week 5)

- Milestone 5: End-User Training & Go-Live (Week 6)

7. High-Level Risk Register

| Risk Description | Impact | Probability | Mitigation Strategy |
| --- | --- | --- | --- |
| Data Quality: Legacy Excel data contains duplicate vendors and outdated pricing. | High | High | Consultant will provide strict CSV templates; Client is responsible for data cleansing prior to import. |
| User Resistance: Sales team may resist moving from email to a CRM system. | Medium | Medium | Engage Rahul Sharma early as a system champion; focus heavily on the "1-click quote" benefit during training to show immediate value. |

8. Deliverables

- Signed Project Charter Document.

- Formal authorization to proceed to the Requirement Gathering phase.

9. Consultant Notes & Best Practices

- Best Practice: Never proceed to configuration without a signed charter. If a client later demands a manufacturing module, the charter serves as the contractual proof that it was marked "Out-of-Scope" and requires a Change Order.

- Best Practice: Keep the objectives measurable (e.g., "Reduce time by 40%"). Vague objectives like "Improve sales" cannot be tested during project closure.